## Sheet1
QUALITY ASSURANCE PLAN
SL. NO | DESCRIPTION | CHARECTERISTICS | CATEGORY | TYPE OF CHECK | FREQUENCY OF CHECK | ACCEPTANCE CRITERIA | INSPECTION |  | FORMAT OF RECORDS | REMARKS
[7 empty] | BY QC | CLIENT
1 | Surveying
a) |  | Co-ordinates/ levels, bench mark | Major | Measurement | Initial | Approved Drawing | I | R | Register
b) |  | Calibration of survey instruments |  | LR | Once in Every 12 Months | As per IS code | I | R | Calibration Certificate
2 | Exavation
a) |  | Layout checking | Major | V | Initial | Approved Drawing | I | R | Register
b) |  | Excavation with proper side slopes, shoring, removing water etc. |  | V | Initial | Approved drawing | I | R | -
c) |  | Checking locations, firm bed, levels, free from slush etc |  | V | Initial | As per specification | I | R | Register
d) |  | Disposal/Stocking of excavated earth |  | V | Initial | As per Instruction by Engineer In Charge | I | R | -
3 | BACK FILLING IN FOUNDATION AND TRENCHES
a) |  | Determining the MDD and OMC | Major | V | Initial | IS 2720 | I | R | LR
b) |  | Filling and Compaction in layers not more than 300mm |  | V | Every layer | As per Specs. | I | R | Checklist
c) |  | Check for degree of compaction |  | V | Every layer | IS 2720 | I | R | Checklist
4 | Anti- Termite Treatment (ATT)
a) |  | Check for rate of application of dosage | Major | V | Initial | As per specification | I | R | MTC
5 | PCC
a) |  | Checking layout, line and level | Major | V | Initial | Approved Drawing | I | R | -
b) |  | Form work and Curing |  | V | Initial | As per specs | I | R | -
6 | DRAWINGS
a) |  | Receiving and Distributing updated drawing to site team | Major | R | Initial | - | I | R | Drawing Issue Register
b) |  | Collecting superseded drawing |  | R | Initial | - | I | R | Drawing Issue Register
7 | CONCRETE REQUIREMENT AND APPROVAL
a |  | Approval of Mix Design | Major | R | Initial | IS 456 | I | R | LR
b |  | Inspection of Fresh Concrete at site |  | V | Every pouring | As Per Approved Mix Design | I | R | Slump Register
8 | FORMWORK
a |  | Preparation of Formwork support plan | Major | R | Initial | As per specifications | I | R | -
b |  | Preparatory works for steel/plywood |  | R | Initial | As per specifications | I | R | Checklist
c |  | Fixing and positioning in location for shuttering works and supports etc |  | V | At execution | Approved Drawing | I | R | Checklist
d |  | Inspection of alignment, verticality, dimensions etc in line with construction drawing |  | V | At execution | Approved Drawing | I | R | Checklist
e |  | Final Inspection of alignment, verticality, dimensions etc in line with construction drawing |  | V | At execution | Approved Drawing | I | R | Checklist
9 | REINFORCEMENT WORKS
a |  | Preparation of BBS in line with construction drawing | Major | R | Initial |  | I | R | BBS
b |  | Straightening/cutting/bending and binding in position as per the drawing |  | V |  |  | I | R | BBS
c |  | Inspection of reinforcement |  | V |  |  | I | R | Checklist
10 | CONCRETING (WALL/SLAB/FOOTING/COLUMN/BEAM ETC)
a |  | Preparation and check temporary arrangements of staging, chute, walkway, machineries etc. | Major | V | At execution | As instructed by Site Engineer | I | R | Checklist
b |  | Ordering concrete as per the requirement in accordance with flow/grade/quantity. |  | V | At execution | Mix Design and Pour Plan | I | R | Checklist
c |  | Inspection of fresh concrete (Slump/flow test, batch slip, batch time etc) |  | V | At execution | Mix Design and Pour Plan | I | R | Register
D |  | Sampling and testing of Concrete cubes |  | V | At execution | IS 456 | I | R | Register
11 | CURING
|  | Curing of Concrete | Major | V | At execution | By Curing compound/water/ or As per specification, | I | R | -
12 | DE-SHUTTERING OF FORMWORK
|  | De-shuttering with adequate precautions | Major | V | At execution | IS 456 / As specified | I | R | Register
13 | POST INSPECTION OF CONCRETE AFTER DE-SHUTTERING
|  | Visual inspection of concrete surface and rectification of defects as per approved methodology. | Major | V | At execution | As per specifications | I | R | -
14 | BRICK/ BLOCK MASONARY
a |  | Procurement of bricks/blocks of approved quality | Major | V | Initial | As per specification | I | R | Invoice
b |  | Inspection of Bricks/Blocks |  | V | Initial | As per specification | I | R | Register
c |  | Shifting and handling bricks/Blocks to the work location with proper care |  | V | At execution | As instructed | I | R | -
d |  | Mixing and preparation of cement mortar, erection of brick/block wall |  | V | At execution | As per specification | I | R | Checklist
e |  | Staging and Scaffolding |  | V | At execution | - | I | R | Checklist
f |  | Final Inspection of bond, joints, thickness, line, levels, verticality etc |  | V | At execution | Approved Drawing | I | R | Checklist
g |  | Curing of brick work |  | V | At execution | - | I | R | -
15 | PLASTERING
a |  | Preparatory arrangements of surface preparation (raking of joints/removal of loose mortar/fixing chicken mesh etc | Major | V | At execution | As per specifications | I | R | Checklist
b |  | Proportion of cement mortar, mixing and placing in location |  | V | At execution | Drawing/Specifications | I | R | Checklist
c |  | Checking of alignment, thickness, verticality etc in line of construction drawing |  | V | At execution | Drawing/Specifications | I | R | Checklist
d |  | Curing for the Plastering work |  | V | At execution | - | I | R | -
16 | WOOD WORKS
a |  | Inspection of wood (Door frame/shutters) | Major | V | At execution | As per drawing/ specification | I | R | Invoice
b |  | Inspection of workmanship |  | V | At execution | As per drawing/ specification | I | R | Checklist
17 | ALUMINIUM DOORS AND WINDOWS
a |  | Sample approval | Major | V |  | - | I | R | Invoice
b |  | Inspection of materials |  | V | At execution | As per drawing/ specification | I | R | Checklist
c |  | Inspection of workmanship |  | V | At execution | As per drawing/ specification | I | R | Checklist
18 | STEEL FABRICATION WORKS
a |  | Inspection of materials | Major | V |  | As per drawing/ specification | I | R | Invoice
b |  | Inspection of workmanship |  | V | At execution | As per drawing/ specification | I | R | Checklist
c |  | Welding |  | V | At execution | As per approved procedure | I | R | Checklist
d |  | Primer Painting |  | V | At execution | Manufacturer specs | I | R | Checklist
e |  | Erection at site |  | V | At execution | Drawing/Specs | I | R | Checklist
f |  | Alignment / Final Inspection - fabrication |  | V | At execution | Drawing/Specs | I | R | Checklist
g |  | Final Painting |  | V | At execution | Specifications | I | R | Checklist
19 | PAINTING
a |  | Approval of paint sample – brand and shade | Major | V | Initial | As per specification | I | R | Invoice
b |  | Surface preparation prior to painting |  | V | At execution | As per specifications | I | R | Checklist
c |  | Inspection of paint materials |  | V | At execution | As per specification | I | R | Checklist
d |  | Mixing of putty/paint as per manufacturer recommendation and applying number of coats as per the method statement |  | V | At execution | As per specification | I | R | Checklist
e |  | Final visual inspection |  | V | At execution | As per sample | I | R | Checklist
20 | TILE WORKS
a |  | Sample approval |  | V |  | As Specified | I | R | Invoice
b |  | Execution of tile works, Recording batch no of tiles, |  | V | At execution | As Specified | I | R | Checklist
c |  | Final inspection of tiles works |  | V | At execution | As Specified | I | R | Checklist
21 | STONE WORKS (GRANITE / KOTA ETC)
a |  | Approval of Sample | Major | V |  | As specified | I | R | Invoice
b |  | Execution of stone works |  | V | At execution | As per drawing / Specs | I | R | Checklist
c |  | Final Inspection of completed works |  | V | At execution | As per drawing / Specs | I | R | Checklist
22 | WATERPROOFING
a |  | Approval of proposed method statement for waterproofing | Major | V | At execution | As per specification | I | R | -
b |  | Carrying out waterproofing works as per the approved methodology |  | V | At execution | As per specification | I | R | Checklist
c |  | Inspection of waterproofed area for water tightness |  | V | At execution | As per specification | I | R | Checklist
23 | ELECTRICAL WORKS
a |  | Execution of electrical works as per the drawing with approved material | Major | V | At execution | As per specification/ Drawing | I | R | -
b |  | Commissioning of electrical works |  | V | At execution | As per specification | I | R | -
24 | PLUMBING WORKS
a |  | Execution of plumbing works as per the drawing with approved material | Major | V | At execution | As per specification/ Drawing | I | R | Checklist
b |  | Commissioning of plumbing fittings (CP and Sanitary) – Final inspection |  | V | At execution | As per specification | I | R | Checklist
25 | False Ceiling
a |  | Installation with necessary supports, cut out, fixtures etc | Major | V | At execution | Drawing/ Specs | I | R | Checklist
b |  | Final Inspection |  | V | At execution | Drawing/ Specs | I | R | Checklist
26 | PAVER BLOCKS
a |  | Sample Approval | Major | V | Initial | As per Specification | I | R | Invoice
b |  | Fixing of pavers |  | V | At execution | As per drawing | I | R | Checklist
I- Inspection
V- Visual
R- Review
LR- Lab Report
MTC -Manufacturer Test Certificate

## Sheet2
SL.NO | Activity | Code of conformance | Performer / checker | Approver | Surveillance check | Records | Remarks
1 | SURVEY
a) | Co-ordinates/ levels, bench mark | Approved Drawing | Surveyor | Site Engineer | Client | Levelling Register
b) | Calibration of survey instruments | As per IS code | Surveyor | Quality Engineer | Client | Calibration certificate
2 | EXCAVATION
a) | Layout checking | Approved Drawing | Site Engineer | Site Engineer | Random | Joint Record
b) | Excavation with proper side slopes, shoring, removing water etc. | Approved drawing | Site Engineer | Site Engineer |  | Joint Record
c) | Checking locations, firm bed, levels, free from slush etc | As per specification | Foreman | Site Engineer
d) | Disposal/Stocking of excavated earth | As per Instruction by Project In Charge | Foreman | Site Engineer | - | -
3 | BACK FILLING IN FOUNDATION AND TRENCHES
a) | Determining the MDD and OMC | IS 2720 | Site Engineer | QC Engineer | PMC | Soil Report
b) | Filling and Compaction in layers not more than 300mm | As per Specs. | Foreman | Site Engineer | PMC | Check list
c) | Check for degree of compaction | IS 2720 | Site Engineer | QC Engineer | PMC | Check list record
4
a) | Check for rate of application of dosage | As per specification | Specialized agency | Site Engineer | Construction manager | Check list
5 | PCC
a) | Checking layout, line and level | Approved Drawing | Foreman | QC Engineer | PMC | Check list
b) | Form work and Curing | As per specs | Foreman | Site Engineer
6 | DRAWINGS
a) | Receiving and Distributing updated drawing to site team | - | Document Controller/ As designated | PMC Team | Record | Drawing Register
b) | Collecting superseded drawing | - | Document Controller/ As designated | PMC Team | Record | Drawing Register
7 | CONCRETE REQUIREMENT AND APPROVAL
a | Approval of Mix Design | IS 456 | QC Engineer/ Site Engineer | Construction manager & PMC | Witness | Design Mix and Trial sheets
b | Inspection of Fresh Concrete at site | As Per Approved Mix Design | QC Technician | QC engineer | Witness | Record – Daily Concrete report
8 | FORMWORK
a | Preparation of Formwork support plan | As per specifications | Project In Charge | PD | - | Record
b | Preparatory works for steel/plywood | As per specifications | Foreman | Site Engineer | Random | -
c | Fixing and positioning in location for shuttering works and supports etc | GFC Drawing | Foreman | Site Engineer | Random | -
d | Inspection of alignment, verticality, dimensions etc in line with construction drawing | GFC Drawing | Foreman | Site Engineer | Random | -
e | Final Inspection of alignment, verticality, dimensions etc in line with construction drawing | GFC Drawing | Site Engineer | QC Engineer | Witness | Pour card
9 | REINFORCEMENT WORKS
a | Preparation of BBS in line with construction drawing | GFC Drawing | Site Engineer | Project In charge/Billing Engineer | - | BBS
b | Straightening/cutting/bending and binding in position as per the drawing | GFC Drawing | Foreman | Site Engineer | Random
c | Inspection of reinforcement | GFC drawing | Site Engineer | QC engineer | witness | Check list
10 | CONCRETING (WALL/SLAB/FOOTING/COLUMN/BEAM ETC)
a | Preparation and check temporary arrangements of staging, chute, walkway, machineries etc. | As instructed by Site Engineer | Foreman | Site Engineer | - | -
b | Ordering concrete as per the requirement in accordance with flow/grade/quantity. | Mix Design and Pour Plan | Site Engineer | Project in charge | Witness | -
c | Inspection of fresh concrete (Slump/flow test, batch slip, batch time etc) | Mix Design and Pour Plan | Foreman/QC Lab technician | QC Engineer | Witness | Record – daily concrete report
D | Sampling and testing of Concrete cubes | IS 456 | QC Lab technician | QC Engineer | Witness | Record – Compressive Strength record
11 | CURING
| Curing of Concrete | By Curing compound/water/ or As per specification, | Foreman / Site Engineer | QC Engineer | witness | Record – Curing form
12 | DE-SHUTTERING OF FORMWORK
| De-shuttering with adequate precautions | IS 456 / As specified | Foreman / Site Engineer | QC Engineer | witness | Record – De-shuttering form | As per “Pour Plan”
13 | POST INSPECTION OF CONCRETE AFTER DE-SHUTTERING
| Visual inspection of concrete surface and rectification of defects as per approved methodology. | As per specifications | Foreman / Site Engineer | QC Engineer | witness | -
14 | BRICK/ BLOCK MASONARY
a | Procurement of bricks/blocks of approved quality | As per specification | Site Engineer / PMC | Construction manager | Random
b | Inspection of Bricks/Blocks | As per specification | Lab Technician | QC engineer | Witness | Record
c | Shifting and handling bricks/Blocks to the work location with proper care | As instructed | Foreman | Site Engineer | Random
d | Mixing and preparation of cement mortar, erection of brick/block wall | As per specification | Foreman | Site Engineer | Random | -
e | Staging and Scaffolding | - | Foreman | Safety Supervisor | Random
f | Final Inspection of bond, joints, thickness, line, levels, verticality etc | GFC Drawing | Site Engineer | QC Engineer | Witness | Record
g | Curing of brick work | - | Foreman/ Site Engineer | QC Engineer | Witness | Record
15 | PLASTERING
a | Preparatory arrangements of surface preparation (raking of joints/removal of loose mortar/fixing chicken mesh etc | As per specifications | Foreman | Site Engineer | Random | -
b | Proportion of cement mortar, mixing and placing in location | Drawing/Specifications | Foreman | Site Engineer | Random
c | Checking of alignment, thickness, verticality etc in line of construction drawing | Drawing/Specifications | Foreman / Site Engineer | QC engineer | Random | -
d | Curing for the Plastering work | - | Foreman / Site Engineer | QC engineer | Random
16 | WOOD WORKS
a | Inspection of wood (Door frame/shutters) | As per drawing/ specification | QC Lab technician | QC Engineer | Witness | Record- Field test report
b | Inspection of workmanship | As per drawing/ specification | Foreman / Site Engineer | QC Engineer | Witness | Record- Check list
17 | ALUMINIUM DOORS AND WINDOWS
a | Sample approval | - | Construction Manager | PD / Architect | -
b | Inspection of materials | As per drawing/ specification | Specialized agency | Site Engineer | Witness | -
c | Inspection of workmanship | As per drawing/ specification | Specialized agency | Site Engineer | Witness | -
18 | STEEL FABRICATION WORKS
a | Inspection of materials | As per drawing/ specification | Foreman (P & M) | Site Engineer | Witness | -
b | Inspection of workmanship | As per drawing/ specification | Foreman | Site Engineer | Witness | -
c | Welding | As per approved procedure | Foreman | Site Engineer | Random
d | Primer Painting | Manufacturer specs | Foreman | Site Engineer | Random
e | Erection at site | Drawing/Specs | Foreman | Site Engineer | Random
f | Alignment / Final Inspection - fabrication | Drawing/Specs | Site Engineer | QC Engineer | Witness | Record
g | Final Painting | Specifications | Foreman | Site Engineer | Random
19 | PAINTING
a | Approval of paint sample – brand and shade | As per specification | Construction manager | PD /Architect | Witness | Record
b | Surface preparation prior to painting | As per specifications | Foreman / Site Engineer |  | Witness | Record – check list
QC Engineer
c | Inspection of paint materials | As per specification | Foreman / Site Engineer |  | Witness | Record – Field test report
QC Engineer
d | Mixing of putty/paint as per manufacturer recommendation and applying number of coats as per the method statement | As per specification | Foreman / Site Engineer |  | Witness | Record – Check list
QC Engineer
e | Final visual inspection | As per sample | Site Engineer | QC engineer | Witness | Record
20 | TILE WORKS
a | Sample approval | As Specified | Construction manager | PD
b | Execution of tile works, Recording batch no of tiles, | As Specified | Foreman | Site Engineer
c | Final inspection of tiles works | As Specified | Site Engineer | QC Engineer
21 | STONE WORKS (GRANITE / KOTA ETC)
a | Approval of Sample | As specified | Construction Manager | PD | Witness | Record
b | Execution of stone works | As per drawing / Specs | Foreman | Site Engineer | Witness | -
c | Final Inspection of completed works | As per drawing / Specs | Site Engineer | QC Engineer | Witness | Record
22 | WATERPROOFING
a | Approval of proposed method statement for waterproofing | As per specification | Construction manager | Quality in Charge/ PD
b | Carrying out waterproofing works as per the approved methodology | As per specification | Foreman | Site Engineer | Random | -
c | Inspection of waterproofed area for water tightness | As per specification | Site Engineer | QC Engineer | Witness | Record – Check list
23 | ELECTRICAL WORKS
a | Execution of electrical works as per the drawing with approved material | As per specification/ Drawing | Foreman | Site Engineer | Random | -
b | Commissioning of electrical works | As per specification | Site Engineer | QC engineer / Construction manager | Witness | Record
24 | PLUMBING WORKS
a | Execution of plumbing works as per the drawing with approved material | As per specification/ Drawing | Foreman | Site Engineer | Random | -
b | Commissioning of plumbing fittings (CP and Sanitary) – Final inspection | As per specification | Site Engineer | QC engineer / Construction manager | Witness | Record
25 | False Ceiling
a | Installation with necessary supports, cut out, fixtures etc | Drawing/ Specs | Foreman | Site Engineer | Random | -
b | Final Inspection | Drawing/ Specs | Site Engineer | QC Engineer | Witness | Joint Record
26 | PRE HAND OVER INSPECTION – PUNCH LIST
| Inspection of buildings after completion of all finishing activities | As per approved mock up building | Site Engineer | QC Engineer | Witness | Record
27 | HANDING OVER
a | Completion of snags | As per snag report | Foreman | Site Engineer | PD | Record
b | Final inspection | As per snag report | Site Engineer | QC Engineer | PMC | Record
28 | SNAG ANALYSIS
| Snag analysis after completion of pre-handover snag report | Snag Report | QC Engineer at site | QC in charge | - | Record
29 | Lift Works – N/A for this project
a | Approval for make of lift | As Specified | Construction manager | PD |  |  | Not applicable in this project
b | Erection of lift | As per drawing | Specialized Agency | Construction manager
c | Final inspection of lift | As per drawing | Specialized Agency | Construction manager
30 | STP
| Execution of STP walls and slab | As per drawing | Site Engineer | Construction manager
31 | PAVER BLOCKS
a | Sample Approval | As per Specification | Construction manager | PD
b | Fixing of pavers | As per drawing | Specialized agency/foreman